## Sheet1
http://www.smartsheet.com/blog/gantt-chart-excel
Task | Est. Start Date | Est. End Date | Est. Duration (days) | Act. Start Date | Act. End Date | Act. Duration (days) | Est. Time(h) | Act. Time(h) | Act. Time/ Est. Time(%) | Progress | Calc. Total Time(h) | Eric Ahlström | John Bergsten | Lucas Holmqvist | Christian Markovicz | Konrad Öhman | Week | Dependency
Lecture(1) | 2014-01-20 | 2014-01-20 | 1 | 2014-01-20 | 2014-01-20 | 1 | 10 | 10 | 100% | 100% | 10 | 2 | 2 | 2 | 2 | 2 | 1
Gameplay Design (1) | 2014-01-20 | 2014-01-23 | 4 | 2014-01-20 | 2014-01-20 | 1 | 2 | 2 | 100% | 100% | 2 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1
Achitecture/Design (1) | 2014-01-21 | 2014-01-23 | 3 | 2014-01-21 | 2014-01-23 | 3 | 48 | 48 | 100% | 100% | 48 | 10 | 8 | 10 | 10 | 10 | 1
Architecture Main Design | 2014-01-21 | 2014-01-21 | 1 | 2014-01-21 | 2014-01-21 | 1 | 14 | 14 | 100% | 100% | 14 | 3 | 2 | 3 | 3 | 3 | 1 | Gameplay Design (1)
Domain Model Design | 2014-01-21 | 2014-01-22 | 2 | 2014-01-21 | 2014-01-22 | 2 | 14 | 14 | 100% | 100% | 14 | 3 | 2 | 3 | 3 | 3 | 1 | Gameplay Design (1)
Game-Specific Subsystem | 2014-01-22 | 2014-01-23 | 2 | 2014-01-22 | 2014-01-22 | 1 | 5 | 5 | 100% | 100% | 5 | 1 | 1 | 1 | 1 | 1 | 1 | Domain Model Design
Gameplay foundations | 2014-01-22 | 2014-01-23 | 2 | 2014-01-22 | 2014-01-22 | 1 | 5 | 5 | 100% | 100% | 5 | 1 | 1 | 1 | 1 | 1 | 1 | Domain Model Design
Low-level Renderer | 2014-01-22 | 2014-01-23 | 2 | 2014-01-22 | 2014-01-22 | 1 | 5 | 5 | 100% | 100% | 5 | 1 | 1 | 1 | 1 | 1 | 1 | Domain Model Design
Colission and physics | 2014-01-22 | 2014-01-23 | 2 | 2014-01-22 | 2014-01-22 | 1 | 2.5 | 2.5 | 100% | 100% | 2.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | Domain Model Design
Audio | 2014-01-22 | 2014-01-23 | 2 | 2014-01-23 | 2014-01-23 | 1 | 2.5 | 2.5 | 100% | 100% | 2.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | Domain Model Design
Wbs (1) | 2014-01-23 | 2014-01-23 | 1 | 2014-01-23 | 2014-01-23 | 1 | 3 | 7 | 233.3% | 100% | 7 | 3 | 0 | 0 | 3 | 1 | 1
Writing L1 | 2014-01-23 | 2014-01-23 | 1 | 2014-01-23 | 2014-01-23 | 1 | 12 | 21 | 175% | 100% | 21 | 2 | 4 | 5 | 4 | 6 | 1 | Rows 5-11
Meeting(week 1) | 2014-01-20 | 2014-01-24 | 5 | 2014-01-20 | 2014-01-24 | 5 | 10 | 10 | 100% | 100% | 10 | 2 | 2 | 2 | 2 | 2 | 1
Total L1 | 2014-01-20 | 2014-01-24 | 5 | 2014-01-28 | 2014-02-01 | 5 | 85 | 98 | 115.3% | 100% | 98 | 19.4 | 16.4 | 19.4 | 21.4 | 21.4 | 1
R1 (Weekly Report) | 2014-01-26 | 2014-01-26 | 1 | 2014-01-26 | 2014-01-26 | 1 | 10 | 8 | 80% | 100% | 8 | 2 | 0 | 2 | 2 | 2 | 2
Detailed L1 | 2014-01-27 | 2014-01-30 | 4 | 2014-01-27 | 2014-01-30 | 4 | 44 | 43 | 97.73% | 100% | 43 | 8 | 9.5 | 8.5 | 8.5 | 8.5 | 2
Class Diagram | 2014-01-27 | 2014-01-30 | 4 | 2014-01-27 | 2014-01-30 | 4 | 30 | 29 | 96.67% | 100% | 29 | 4 | 8.5 | 7.5 | 4.5 | 4.5 | 2 | Rows 5-11
Sequence Diagram | 2014-01-27 | 2014-01-30 | 4 | 2014-01-27 | 2014-01-30 | 4 | 8 | 8 | 100% | 100% | 8 | 2 | 1 | 1 | 2 | 2 | 2 | Rows 5-11
State Machine | 2014-01-27 | 2014-01-30 | 4 | 2014-01-27 | 2014-01-30 | 4 | 6 | 6 | 100% | 100% | 6 | 2 | 0 | 0 | 2 | 2 | 2 | Rows 5-11
Architecture/Design (2) | 2014-01-27 | 2014-01-30 | 4 |  |  | 1 | 0 | 0 | 100% |  | 0 | [5 empty] | 2
Gameplay Design (2) | 2014-01-27 | 2014-01-30 | 4 | 2014-01-27 | 2014-01-30 | 4 | 2 | 12.5 | 625% | 100% | 12.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2
Lecture(2) | 2014-01-31 | 2014-01-31 | 1 | 2014-01-31 | 2014-01-31 | 1 | 10 | 10 | 100% | 100% | 10 | 2 | 2 | 2 | 2 | 2 | 2 | Lecture(1)
Writing L2 | 2014-01-31 | 2014-01-31 | 1 | 2014-01-31 | 2014-01-31 | 1 | 10 | 4.5 | 45% | 80% | 5.63 |  | 1.5 | 1.5 |  | 1.5 | 2 | Rows 18-20
Changes in L1 | 2014-01-31 | 2014-01-31 | 1 | 2014-01-31 | 2014-01-31 | 1 | 5 | 0 | 0% | 0% | 0 | [5 empty] | 2 | Feedback on L1
Wbs (2) | 2014-01-31 | 2014-01-31 | 1 | 2014-01-31 | 2014-01-31 | 1 | 2 | 3.5 | 175% | 100% | 3.5 | 3 |  |  | 0.5 |  | 2
Meeting(week 2) | 2014-01-27 | 2014-01-31 | 5 | 2014-01-27 | 2014-01-31 | 5 | 10 | 10 | 100% | 100% | 10 | 2 | 2 | 2 | 2 | 2 | 2
Total L2 | 2014-01-27 | 2014-01-31 | 5 | 2014-01-27 |  | -41665 | 93 | 91.5 | 98.39% | 90% | 101.67 | 19.5 | 17.5 | 18.5 | 17.5 | 18.5 | 2
R2 (Weekly Report) | 2014-02-02 | 2014-02-02 | 1 | 2014-01-31 | 2014-01-31 | 1 | 10 | 7 | 70% | 0% | 0 | 1 | 0.5 | 2 | 1.5 | 2 | 3
Lecture (3) | 2014-02-03 | 2014-02-03 | 1 | 2014-02-03 | 2014-02-03 | 1 | 10 | 10 | 100% | 0% | 0 | 2 | 2 | 2 | 2 | 2 | 3 | Lecture(2)
Meeting(week 3) | 2014-02-05 | 2014-02-07 | 3 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 3
Resources | 2014-02-03 | 2014-02-06 | 4 |  |  | 1 | 15 | 0 | 0% | 0% | 0 | [5 empty] | 3
Low-level Renderer | 2014-02-03 | 2014-02-06 | 4 |  |  | 1 | 40 | 0 | 0% | 0% | 0 | [5 empty] | 3
Player Movement | 2014-02-03 | 2014-02-03 | 1 |  |  | 1 | 8 | 0 | 0% | 0% | 0 | [5 empty] | 3
Objects | 2014-02-04 | 2014-02-04 | 1 |  |  | 1 | 8 | 0 | 0% | 0% | 0 | [5 empty] | 3
AI | 2014-02-05 | 2014-02-05 | 1 |  |  | 1 | 8 | 0 | 0% | 0% | 0 | [5 empty] | 3
Map Loader | 2014-02-06 | 2014-02-06 | 1 |  |  | 1 | 8 | 0 | 0% | 0% | 0 | [5 empty] | 3
Screens | 2014-02-07 | 2014-02-07 | 1 |  |  | 1 | 8 | 0 | 0% | 0% | 0 | [5 empty] | 3
Gameplay foundations | 2014-02-03 | 2014-02-07 | 5 |  |  | 1 | 40 | 0 | 0% | 0% | 0 | [5 empty] | 3
Debugging | 2014-02-07 | 2014-02-07 | 1 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 3
R3 (Weekly Report) | 2014-02-09 | 2014-02-09 | 1 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 4
Meeting(week 4) | 2014-02-10 | 2014-02-10 | 1 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 4
Lecture(4) | 2014-02-10 | 2014-02-13 | 4 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 4 | Lecture (3)
Audio | 2014-02-07 | 2014-02-14 | 8 |  |  | 1 | 50 | 0 | 0% | 0% | 0 | [5 empty] | 4 | Rows 34-38
Visual Effects | 2014-02-10 | 2014-02-14 | 5 |  |  | 1 | 50 | 0 | 0% | 0% | 0 | [5 empty] | 4 | Rows 34-38
R4 | 2014-02-16 | 2014-02-16 | 1 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 5
Lecture(5) | 2014-02-17 | 2014-02-17 | 1 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 5 | Lecture(4)
Collision and Physics | 2014-02-07 | 2014-02-17 | 11 |  |  | 1 | 35 | 0 | 0% | 0% | 0 | [5 empty] | 5 | Rows 34-38
Meeting(week 5) | 2014-02-17 | 2014-02-19 | 3 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 5
Front End | 2014-02-17 | 2014-02-19 | 3 |  |  | 1 | 30 | 0 | 0% | 0% | 0 | [5 empty] | 5 | Rows 34-38
Optimization | 2014-02-18 | 2014-02-19 | 2 |  |  | 1 | 20 | 0 | 0% | 0% | 0 | [5 empty] | 5 | Front End
Documentation | 2014-02-18 | 2014-02-21 | 4 |  |  | 1 | 20 | 0 | 0% | 0% | 0 | [5 empty] | 5 | Front End
Record Prototype | 2014-02-20 | 2014-02-21 | 2 |  |  | 1 | 20 | 0 | 0% | 0% | 0 | [5 empty] | 5 | Front End
Total L3 | 2014-02-03 | 2014-02-21 | 19 |  |  | 1 | 371 | 0 | 0% | 0% | 0 | 3 | 2.5 | 4 | 3.5 | 4 | 5
R5 (Weekly Report) | 2014-02-23 | 2014-02-23 | 1 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 6
Meeting(week 6) | 2014-02-24 | 2014-02-24 | 1 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 6
Lecture(6) | 2014-02-24 | 2014-02-25 | 2 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 6
Balancing | 2014-02-24 | 2014-02-26 | 3 |  |  | 1 | 20 | 0 | 0% | 0% | 0 | [5 empty] | 6 | Total L3
Modding | 2014-02-24 | 2014-02-26 | 3 |  |  | 1 | 30 | 0 | 0% | 0% | 0 | [5 empty] | 6 | Total L3
Update L1,L2 & L3 | 2014-02-24 | 2014-02-28 | 5 |  |  | 1 | 15 | 0 | 0% | 0% | 0 | [5 empty] | 6 | L1,L2 & L3
Evaluations | 2014-02-27 | 2014-02-28 | 2 |  |  | 1 | 50 | 0 | 0% | 0% | 0 | [5 empty] | 6
R6 (Weekly Report) | 2014-03-02 | 2014-03-02 | 1 |  |  | 1 | 10 | 0 | 0% | 0% | 0 | [5 empty] | 7
Progress Report | 2014-03-03 | 2014-03-03 | 1 |  |  | 1 | 25 | 0 | 0% | 0% | 0 | [5 empty] | 7
Total L4 | 2014-02-24 | 2014-03-03 | 8 |  |  | 1 | 170 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 7
Total Project | 2014-01-14 | 2014-03-03 |  |  |  |  | 564 | 8 |  |  | 0 | 5 | 3.5 | 5 | 5.5 | 6
Added
Removed